## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project setup and environment configuration | MUST HAVE | No Dependency | Pragatheeshvaran R | 3- Completed
S1 | S1 | US-002 | Nmap integration for network scanning | MUST HAVE | Nmap | Pragatheeshvaran R | 3- Completed
S2 | S2 | US-003 | Parse scan results and extract open ports | MUST HAVE | scanner.py | Pragatheeshvaran R | 3- Completed
S2 | S2 | US-004 | Integrate VirusTotal API for threat intelligence | MUST HAVE | requests | Pragatheeshvaran R | 3- Completed
S3 | S3 | US-005 | Develop risk scoring system | MUST HAVE | analyser.py | Pragatheeshvaran R | 3- Completed
S3 | S3 | US-006 | Store scan results in database | MUST HAVE | SQLite | Pragatheeshvaran R | 3- Completed
S4 | S4 | US-007 | Develop Streamlit dashboard | MUST HAVE | Streamlit | Pragatheeshvaran R | 3- Completed
S4 | S4 | US-008 | Visualization using Plotly | SHOULD HAVE | Plotly | Pragatheeshvaran R | 3- Completed
S5 | S5 | US-009 | Email alerts for high-risk vulnerabilities | SHOULD HAVE | SMTP | Pragatheeshvaran R | 3- Completed
S5 | S5 | US-010 | Testing and final integration | MUST HAVE | All modules | Pragatheeshvaran R | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 45 | 1 | 1 | 2 | 2 | 5 | 4 | 4 | 4 | 5 | 4 | 4 | 6 | 2 | 1
SPRINT 1 BACKLOG
US-001 | 1 | Project setup and environment configuration | 2026-03-01 | 2026-03-02 | Pragatheeshvaran R | Design | completed | 2 | bar: Day 1 to Day 2
US-002 | 2 | Nmap integration for network scanning | 2026-03-03 | 2026-03-04 | Pragatheeshvaran R | Coding | completed | 4 | Day 3: 2; Day 4: 2
US-003 | 3 | Parse scan results and extract open ports | 2026-03-05 | 2026-03-06 | Pragatheeshvaran R | Coding | completed | 5 | Day 5: 3; Day 6: 2
US-004 | 4 | Integrate VirusTotal API for threat intelligence | 2026-03-07 | 2026-03-08 | Pragatheeshvaran R | Coding | completed | 4 | Day 7: 2; Day 8: 2
US-005 | 5 | Develop risk scoring system | 2026-03-09 | 2026-03-10 | Pragatheeshvaran R | Coding | completed | 5 | Day 9: 3; Day 10: 2
US-006 | 6 | Store scan results in database | 2026-03-11 | 2026-03-13 | Pragatheeshvaran R | Coding | completed | 5 | Day 11: 2; Day 12: 3
US-007 | 7 | Develop Streamlit dashboard | 2026-03-14 | 2026-03-17 | praveenkumar v | Design | completed | 6 | Day 5: 2; Day 6: 2; Day 7: 2
US-008 | 8 | Visualization using Plotly | 2026-03-18 | 2026-03-20 | praveenkumar v | Coding | completed | 4 | Day 8: 2; Day 9: 2
US-009 | 9 | Email alerts for high-risk vulnerabilities | 2026-03-21 | 2026-03-23 | Pragatheeshvaran R | Coding | completed | 4 | Day 10: 2; Day 11: 2
US-010 | 10 | Testing and final integration | 2026-03-24 | 2026-03-26 | Pragatheeshvaran R | Testing | completed | 6 | Day 12: 3; Day 13: 2; Day 14: 1

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on project requirements | Discussed with mentor and clarified requirements
Sprint 1 | Day 4 | Confusion in workflow and module design | Team discussion and finalized architecture
Sprint 1 | Day 6 | Difficulty in Nmap integration | Referred documentation and fixed issues
Sprint 1 | Day 8 | issue in parsing scan results | Debugged code and corrected logic
Sprint 1 | Day 10 | API errors in VirusTotal integration | Fixed API handling and tested again
Sprint 1 | Day 12 | Delay in dashboard UI development | Coordinated with teammate, reviewed UI requirement
Sprint 1 | Day 16 | Issues in email alerts | Debugged SMTP and verified functionality
Sprint 1 | Day 18 | Testing issues and integration bugs | Performed final testing and resolved errors

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-03-01 | 2026-03-10 | Pragatheeshvaran R | Writing clean and structured code | Assuming requirements without confirmation | Regular team discussions | Clarified requirements with mentor and improved workflow
2 | Sprint 1 | 2026-03-01 | 2026-03-10 | Praveenkumar V | Improving UI design | Delaying frontend tasks | Dashboard development | Completed UI and improved visualization
3 | Sprint 1 | 2026-03-24 | 2026-03-26 | pragatheeshvaran R,praveenkumar v | Final testing and validation | Ignoring minor bugs | Proper documentation | Completed testing and finalized project
4
5
6
7